MUSTAFA'S AI AGENCY Step-by-Step Execution Plan Built specifically for your skills: 6 yrs AI engineering ¦ Agentic systems ¦ LLMs & RAG ¦ Full-stack ¦ Sales & client closing

Why This Plan Is Different From Generic Agency Advice Most agency plans assume you need to learn AI first. You don't you built it professionally for 6 years. Your actual bottleneck is NOT skills, NOT delivery, NOT confidence in the tech. Your bottleneck is: you haven't yet monetized your stack at scale. This plan fixes that. You also have sales and client-closing skills you've barely used. That is your second unfair advantage. This plan treats you as what you are: a technical founder who needs to become a commercial operator.

| PHASE 1 Define Your Highest-Value Offer | Days 1–7 |
| --- | --- |

You can build almost anything. That's actually a problem right now because trying to offer everything means clients don't know what to buy. Your first job is ruthless focus: one niche, one outcome, one price.

Step 1 Pick the ONE Niche You'll Dominate

Based on your background, these three niches are the strongest fit for you specifically:

|  | Niche | Why You Win Here | Avg Deal Size |
| --- | --- | --- | --- |
| ★ Best | Enterprise & Gov (KSA/Gulf region) | Air-gapped RAG + Arabic LLMs = rare skill set. Your Navid experience is proof. | $10K–$50K projects |

Your air-gapped RAG + Arabic embedding expertise is a category of one. Almost no freelancer or agency can match it.

Step 2 — Define ONE Productized Service

Don't say 'I build AI systems.' Say something specific and outcome-focused. Examples:

- "We deploy a fully private, air-gapped AI knowledge system on your servers in 30 days no data leaves your infrastructure."

Pick one. Name it. Give it a delivery timeline and a measurable outcome. This becomes your anchor offer.

Phase 1 Exit Criteria ✓ You have a named service with a clear outcome and timeline ✓ You can explain your offer in 2 sentences to any business owner

| PHASE 2 Build Your Proof Asset & Pricing | Days 8–14 |
| --- | --- |

You already have real project experience. Now you need to convert that into commercial proof that closes deals. This is the bridge between 'I'm an engineer' and 'I run an agency.'

Step 4 — Set Pricing That Reflects Your Seniority

You are not a junior freelancer. You are a 6-year AI engineer who has delivered enterprise systems. Price accordingly.

| Offer Type | Price Range | When to Use |
| --- | --- | --- |
| Monthly Retainer | $3,000–$6,000/month | Ongoing agent ops, RAG maintenance, updates |
| Project / Build Fee | $8,000–$25,000 one-time | Air-gapped deployments, custom AI infrastructure |
| Hybrid (Best) | $5K setup + $2K–$3K/month | Build the system, then maintain and improve it |

Step 5 — Create a 2-Page Offer Document

This is your sales weapon. One document that does the selling for you before and during a call. Include:

- Page 1: The problem your niche has, your solution name, how it works in 3 steps, and one case study.

- Page 2: What's included, timeline, price, and a clear CTA ("Book a 30-min call").

Use Claude or GPT-4 to write the copy. You provide the technical facts; AI polishes the language.

Phase 2 Exit Criteria ✓ At least 1 written case study with real or estimated metrics ✓ Pricing set at $3,000/month minimum or $8,000+ per project ✓ A 2-page offer PDF ready to send to any prospect

| PHASE 3 Land Your First 3 Paying Clients | Weeks 3–8 |
| --- | --- |

This is where your sales and client-closing skills the ones you've barely used — finally get deployed at full power. No ads needed. Pure direct outreach.

Build a Targeted Prospect List of 150–200 Leads

For Gulf/Enterprise niche:

- Search LinkedIn for: 'IT Director', 'CTO', 'Digital Transformation' at mid-to-large firms in KSA, UAE, Qatar

- Target industries: energy, legal, government contractors, healthcare, real estate developers

- Use Apollo.io or LinkedIn Sales Navigator to pull contact data

- Use an AI agent (you can build this in an afternoon) to research each company and personalize outreach

For HR/Recruitment niche:

- Target: HR Directors and Heads of Talent Acquisition at companies with 100+ employees

- Use LinkedIn, Apollo.io, or Hunter.io to find direct emails

Step 7 — Run a Direct Outreach Campaign

You have communication and closing skills. Use them. Send personalized messages — not mass spam.

Outreach Message Formula Line 1 (Hook): Reference something specific about their business — a recent hire, a growth announcement, a problem in their industry. Line 2 (Outcome): 'We help [type of company] automate [specific pain point] using AI agents — typically saving [X hours/week] or reducing [Y cost].' Line 3 (Proof): 'We recently built this for [similar company type] — happy to share how it worked.' Line 4 (CTA): 'Worth a 20-minute call this week?' — simple, low-commitment ask.

- Send 15–25 personalized outreach messages per day (LinkedIn DM, Email, or WhatsApp where appropriate)

- Follow up on Day 3 and Day 7 for non-replies

- Track all outreach in a simple Airtable or Notion CRM

Step 8 — Run Tight 30-Minute Closing Calls

Your goal on the call is NOT to explain your tech. It is to understand their pain and match it to your outcome.

- Ask: 'What is your biggest operational bottleneck right now?'

- Ask: 'What have you tried? What didn't work?'

- Ask: 'If we solved this in 30 days, what would that be worth to you?'

- Present your offer. Show the case study. Give the price clearly — no hedging.

- Close: 'I can start next week. Here's the onboarding link and first invoice.'

Objection Handling (Your Most Common Ones) 'It's too expensive' → 'What ROI would you need to see to make this worthwhile?' Then anchor to their answer. 'We need to think about it' → 'What specifically is unclear? I'd rather address it now than waste your time.' 'We already have a vendor' → 'Happy to hear that. What does their air-gapped deployment capability look like?' (They usually don't have one.) 'We don't have budget' → 'Understood. When does your next budget cycle open? Can I send you something to share internally?'

Phase 3 Exit Criteria ✓ 3–5 paying clients signed ✓ Minimum $9,000–$15,000/month in contracted recurring revenue ✓ Your AI delivery system is running client work with minimal manual input from you

| PHASE 4 Systemize Your AI Delivery Stack | Weeks 6–12 |
| --- | --- |

Here is where most agencies get destroyed: they sign clients, then drown in delivery. You have the technical skills to avoid this entirely. Before you take on more than 5 clients, lock your delivery system.

Step 11 — Leverage Your Small Team

You mentioned you have a small team. Use them strategically, not operationally:

- Assign one person as Client Success they handle check-in messages and surface issues to you

- You focus on: new sales, system architecture improvements, and high-complexity client problems

- Nobody on your team should be doing work that an AI agent can do.

Phase 4 Exit Criteria ✓ 90%+ of client fulfillment is automated through your agent stack ✓ You can onboard a new client in under 3 hours of your own time ✓ You have a live ops dashboard showing all client statuses ✓ You are spending under 2 hours/day on delivery across all clients

| PHASE 5 Scale Revenue to $50K+/Month | Months 4–8 |
| --- | --- |

With a proven offer, real client results, and an automated delivery system, you now have something most agencies never build: a scalable, compounding AI infrastructure business. Here's how to grow it.

Step 12 — Stack Your Case Studies Into a Content Engine

You have results. Now broadcast them. Pick ONE platform — LinkedIn is the best fit for your B2B enterprise niche.

- Post 3x per week: one post about a client result, one about an AI insight, one about a system you built

- Use short-form video to show your agent workflows this builds authority faster than text

- Every post should make a CTO or IT Director think: 'I need this person'

- Goal: 10+ inbound leads per week from content within 90 days of consistent posting.

Step 13 — Raise Your Prices as Results Stack Up

- After 3 clients with documented results: raise new client pricing by 30–50%

- After 6 clients: introduce a premium tier at $8,000–$12,000/month for full agentic infrastructure

- Add a $5,000–$15,000 one-time setup/deployment fee for new enterprise clients

- Existing clients: give 60-day notice of price increase — most will stay if results are strong

Step 14 — Add a Second Offer: The AI Audit

This is a low-barrier entry product ($1,500–$3,000) that converts into long-term retainers:

- A 2-week 'AI Readiness Audit' — you assess their current ops and deliver a roadmap for AI automation

- At the end, you present a proposal for implementing the roadmap (your core retainer)

- Conversion rate from Audit to Retainer: typically 60–80% if the audit is high quality

- This works especially well for enterprise prospects who need to 'try before they buy'

Step 15 — The Revenue Math to $50K/Month

| Scenario | Clients | Avg MRR | Monthly Revenue |
| --- | --- | --- | --- |
| Conservative (Month 3) | 5 clients | $3,500 | $17,500/month |
| Target (Month 5) | 10 clients | $4,500 | $45,000/month |
| Stretch (Month 8) | 8 clients + 2 enterprise | $6,500 avg | $52,000/month |

Phase 5 Exit Criteria ✓ One active inbound lead channel producing 5–10 leads/week ✓ 10+ clients at $3,500–$6,000/month average ✓ Your team runs day-to-day delivery — you run strategy and sales ✓ $40,000–$60,000/month in revenue with 60–70% margins

MASTER ROADMAP AT A GLANCE

| # | Phase | Key Actions | Timeline | Revenue Target |
| --- | --- | --- | --- | --- |
| 1 | Define Your Offer | Choose niche (Gulf enterprise), name your service, define outcomes | Days 1–7 | $0 → clarity |
| 2 | Proof & Pricing | Write case studies, set $3K+/mo pricing, build offer PDF | Days 8–14 | $0 → deal-ready |
| 3 | Close Clients | 150 leads, outreach campaign, closing calls | Weeks 3–8 | $9K–$15K/mo |
| 4 | Systemize Delivery | Automate onboarding to reporting with agents + n8n | Weeks 6–12 | $15K–$30K/mo |
| 5 | Scale Revenue | LinkedIn content, price raises, AI Audit offer, team leverage | Months 4–8 | $40K–$60K/mo |

Your Single Biggest Advantage — Don't Waste It Air-gapped RAG on private infrastructure + Arabic LLM support is a category of one in the Gulf market. There are thousands of ChatGPT wrapper agencies. There is almost nobody who can walk into a Saudi government contractor or an energy company and say: 'Your data never leaves your servers, I deploy everything locally, and I support Arabic.' That is you. Lead with that every single time.